## Allocation Plan
Week Number | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Planned
Marcel Notenboom | 8 | 8 | 16 | 16 | 16 | 24 | 24 | 37 | 24 | 24 | 24 | 24 | 24 | 48 | 48 | 48
Gais El-AAsi | 8 | 8 | 16 | 16 | 16 | 24 | 24 | 37 | 24 | 24 | 24 | 24 | 24 | 48 | 48 | 48
Unspecified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Accumulated | 16 | 32 | 64 | 96 | 128 | 176 | 224 | 298 | 346 | 394 | 442 | 490 | 538 | 634 | 730 | 826
Un-planned Hours
0
Week Number | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Actuals
Marcel Notenboom | 8 | 8 | 15 | 17 | 16 | 20 | 26 | 40 | 23 | 22 | 28 | 24 | 22 | 50 | 51 | 53
Gais El-AAsi | 8 | 8 | 10 | 25 | 15 | 22 | 24 | 42 | 20 | 25 | 27 | 20 | 24 | 52 | 58 | 56
Unspecified | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Accumulated | 16 | 32 | 57 | 99 | 130 | 172 | 222 | 304 | 347 | 394 | 449 | 493 | 539 | 641 | 750 | 859
Extra hours
34

## Burnout Chart
Week | Planned | Actuals | Difference
35 | 16 | 16 | 0
36 | 32 | 32 | 0
37 | 64 | 57 | 7
38 | 96 | 99 | 3
39 | 128 | 130 | 2
40 | 176 | 172 | 4
41 | 224 | 222 | 2
42 | 298 | 304 | 6
43 | 346 | 347 | 1
44 | 394 | 394 | 0
45 | 442 | 449 | 7
46 | 490 | 493 | 3
47 | 538 | 539 | 1
48 | 634 | 641 | 7
49 | 730 | 750 | 20
50 | 826 | 859 | 33

## Roadmap
UP | INCEPTION |  |  | ELABORATION | [5 empty] | CONSTRUCTION | [5 empty] | TRANSITION
Project Week | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
Milestones/Deliverables | Project Start - 30/08 |  | User Stories - 11/09 |  | Analysis Final Approval - 19/09 | Architecture - 24/09 | System Diagram - 04/10 | Design Finalisation -15/10 |  | Proof of Concept - 26/10 |  |  |  | Documentation | User Guides | Project/Process Report | Hand In
Requirements/User Stories
Project Introduction
Finalize Requirements
Glossary
Aanalysis
Use Case Diagram
Use Case Descriptions
Activity Diagram
System Sequcen Diagram
Domain Model
Design
Cloud Infrastructure
System Architecture / Component Architecture
Class Diagram
|  |  |  | Tech Stack Decisions |  |  |  | ER Diagram
Design Paterns
UI Design Choices
Implementation
Setup Goolge Project
Setup IoT Core
Connect ESP32 to IoT Core
Setup Skeleton Project Backend
Basic UI and overal system connection
Setup login and user profile
Monitoring electricity consumption with visualisation
Manage devices
Report and device comparation
Ensure a stable and secure connection with the cloud
Ensure correct sensing and calculations for measuring electricity consumption
Find a better solution for extrancting electricity consumption and improve sensitivity
Find a way for the user to setup the device network connection
Overall code cleanup and refactoring for production
Test
Test Cases
Acceptance Tests
System Tests
Unit Testing
Rendering Testing
Usability Testin
System Tests
Acceptance Tests
Documentation
Wrap-up Introduction
Finalze Requirements
Start Writing Analaysis
Use Case
Activity Diagram
Sequence Diagram
Domain Model
Testing
Design Chapter
Architecture
Technologies + CI/CD
Design Patterns
Class Diagram + DB Structrue
Sequence Diagram + UI
Implementation + Tests
Results and Discussions + Conclusions
Process Report
Deployment
Setup and Maintain CI/CD pipelines